## TOC (hidden)
Migration Planning Runbook
Move group:
Event Date:
Table of Contents
Resource Plan
Hour-By-Hour
T-Minus Plan
Server Details
Application Details
Change Control Details
Issues - Action Item
Contacts
Move Event Summary
Relationship Details
Database Details
Server From-To List
Rollback Plan
Risks
Tracker Sheet Wave 00A
Status Update Template
Hypercare Checklist
Glossary
Tracker Sheet Wave 00B

## Hour by Hour(Wave 00B) (hidden)
Hour by Hour Tasks
Task ID | Environment (CMO/FMO) | Migration tasks | Applications | Servers | Owner Group | Owner | Status | Planned Start Time (ET) | Planned Duration | Planned Finish Time (ET) | Actual Start Time (ET) | Actual Finish Time (ET) | Actual Duration | Comments
0 |  | Migration Kickoff Tasks
0.1 | CMO | Open Command Bridge and Take Role | NA | NA | Migration Lead | Karthik | Pending | 7:30 | 5 | 7:35
0.2 | CMO | Ensure Migration Readiness - Final GO/NO-GO | NA | NA | Migration Lead | Karthik | Pending | 7:35 | 5 | 7:40
0.3 | CMO | Confirm Data Replications are completed | NA | NA | Migration Lead | Karthik | Pending | 7:40 | 10 | 7:50
0.4 | CMO | Confirm Backups are completed | NA | NA | Backup Team | TBC | Pending | 7:50 | 10 | 8:00
0.5 | CMO | Confirm T-Minus (T-7 to T-0) are completed | NA | NA | Migration Lead | Karthik | Pending | 8:00 | 5 | 8:05
0.6 | CMO | Disable Alerts | NA | NA | Tools Team | TBC | Pending | 8:05 | 10 | 8:15
0.7 | CMO | Disable the Backup | All | All | Backup Team | TBC | Pending | 8:15 | 15 | 8:30
1 |  | Application Shutdown | [5 empty] | 8:30 | 0 | 8:30
1.1 | CMO | Complete Application Shutdown Tasks | All | All | Application Team | Refer to App Contacts | Pending | 8:30 | 30 | 9:00
1.2 | CMO | Complete Database Shutdown Tasks | All | All | DB Team/App Team | TBC | Pending | 9:00 | 30 | 9:30
1.3 | CMO | Stop the services (various applications) and put them manual startup/Disable mode | All | All | Application Team | Refer to App Contacts | Pending | 9:30 | 15 | 9:45
1.4 | CMO | Verify that all application/database/service shutdown tasks have been completed | All | All | Migration Lead | Karthik | Pending | 9:45 | 15 | 10:00
2 |  | Server Shutdown | [5 empty] | 10:00 | 0 | 10:00
2.1 | CMO | Shutdown the VMs - CMO | All | All | Migration Team | Manjunath | Pending | 10:00 | 30 | 10:30
2.2 | CMO | Ensure that there is no activity on the VMs in CMO | All | All | Migration Team | Manjunath | Pending | 10:30 | 10 | 10:40
2.3 | CMO | Verify that the consistency group is in Active (sync) state between CMO & FMO | All | All | Migration Team | Manjunath | Pending | 10:40 | 20 | 11:00
3 |  | VM Cutover | [5 empty] | 11:00 | 0 | 11:00
3.2 | CMO | Enable Image Access on the CG | All | All | Migration Team | Manjunath | Pending | 11:00 | 30 | 11:30
3.3 | FMO | Power On the VMs of the CG at the FMO | All | All | Migration Team | Manjunath | Pending | 11:30 | 15 | 11:45
3.4 | FMO | Update internal/external DNS / LB entries as required(If Applicable) | All | All | Migration Team | Manjunath/DNS | Pending | 11:45 | 0 | 11:45
3.5 | FMO | Perform any remediation required(If Applicable) | All | All | Migration Team | Manjunath | Pending | 11:45 | 0 | 11:45
3.6 | FMO | Perform server boot healthcheck on VMs | All | All | Migration Team | Manjunath | Pending | 11:45 | 30 | 12:15
3.7 | FMO | Release to OS team for validation | All | All | Migration Team | Manjunath | Pending | 12:15 | 15 | 12:30
3.8 | FMO | Validate server tooling | All | All | Migration Team | Karthik | Pending | 12:30 | 15 | 12:45
3.9 | FMO | Handover Server for User Acceptance Testing | All | All | Migration Team | Karthik | Pending | 12:45 | 10 | 12:55
4 |  | Application Startup | [5 empty] | 12:55 | 0 | 12:55
4.1 | FMO | Complete Database Startup Tasks | All | All | DB Team/App Team | TBC/Refer to App Contacts | Pending | 12:55 | 30 | 13:25
4.2 | FMO | Start the services (various applications) and put them automatic startup mode as required | All | All | Application Team | Refer to App Contacts | Pending | 13:25 | 15 | 13:40 |  |  |  | Service Now is good with Duration
4.3 | FMO | Complete Application Startup Tasks | All | All | Application Team | Refer to App Contacts | Pending | 13:40 | 30 | 14:10
4.4 | FMO | Validate all application startup tasks are complete | All | All | Migration Lead | Karthik | Pending | 14:10 | 10 | 14:20
5 |  | Application Testing / Migration completion | [5 empty] | 14:20 | 0 | 14:20
5.1 | FMO | Complete Operational Application Testing per UAT Document | All | All | Application Team | Refer to App Contacts | Pending | 14:20 | 165 | 17:05 |  |  |  | Filenet 2.45hrs
5.2 | FMO | Validate all application testing completed successfully | All | All | Migration Lead | Karthik | Pending | 17:05 | 15 | 17:20
5.3 | FMO | Enable Direct access on the Consistency Group at FMO | All | All | Migration Team | Manjunath | Pending | 17:20 | 10 | 17:30
5.4 | FMO | Cleanup the Consistency Group in RP4VM | All | All | Migration Team | Manjunath | Pending | 17:30 | 5 | 17:35
5.5 | FMO | Complete Application Testing (Business Testing) |  |  | Application Team | Refer to App Contacts | Pending | 17:35 | 30 | 18:05 | ESB to confir(Abhishek) |  |  | No Business testing for CLB Filenet
5.6 | FMO | Migration Complete Sign Off | All | All | Migration Team | Hemang/Mike | Pending | 18:05 | 5 | 18:10
6 |  | Rollback Steps (Without data changes) | [6 empty] | 0
6.1 | FMO | Stops the services, databases and applications on VMs at FMO | All | All | Application Team | Refer to App Contacts | Pending |  | 5
6.2 | FMO | PowerOff the VMs at the FMO | All | All | Migration Team | Manjunath | Pending |  | 5
6.3 | CMO | Revert back to internal/exteranl DNS entries | All | All | Migration Team | Manjunath/DNS | Pending |  | 15
6.4 | CMO | Power on the VMs art CMO. | All | All | Migration Team | Manjunath | Pending |  | 5
6.5 | CMO | Bring up services & databases | All | All | Application Team | Refer to App Contacts | Pending |  | 15
6.6 | CMO | Bring up the application. | All | All | Application Team | Refer to App Contacts | Pending |  | 15
6.7 | CMO | Complete Application Testing per UAT Document | All | All | Application Team | Refer to App Contacts | Pending |  | 30
7 |  | Rollback Steps (With data changes)
7.1 |  | Repeat migration tasks from 0.1 to 5.5 |  |  | Migration Team | Karthik | Pending

## Tracker Sheet (hidden)
OVERALL STATUS % |  |  | 60.7639 |  | Do Not Migrate (DNM) % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | Pending (By VM %) | 0% | 0% | 44.44% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100%
[5 empty] | In-Progress (By VM %) | 0% | 77.78% | 33.33% | 33.33% | 33.33% | 33.33% | 33.33% | 33.33% | 0% | 33.33% | 33.33% | 33.33% | 33.33% | 33.33% | 0% | 33.33% | 33.33% | 33.33% | 33.33% | 33.33% | 33.33% | 33.33% | 33.33% | 33.33% | 33.33% | 33.33% | 33.33% | 33.33% | 33.33% | 0% | 0% | 0%
Migration Kickoff Tasks |  |  | 58.73% |  | Complete (By VM %) | 100% | 22.22% | 22.22% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 100% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 100% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 0% | 0% | 0%
Application Shutdown |  |  | 75% |  | Do Not Migrate (DNM) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Server Shutdown |  |  | 66.67% |  | Pending (By VM Count) | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9
VM Cutover |  |  | 70.83% |  | In-Progress (By VM Count) | 0 | 7 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0
Application Startup |  |  | 66.67% |  | Complete (By VM Count) | 9 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 9 | 6 | 6 | 6 | 6 | 6 | 9 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0
Application Testing / Migration completion |  |  | 33.33% |  | Total VM Count | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9
Issue Tracker: |  |  |  |  | Planned Duration | 5 | 5 | 10 | 10 | 5 | 10 | 15 | 30 | 30 | 15 | 15 | 30 | 10 | 20 | 30 | 15 | 0 | 0 | 30 | 15 | 15 | 10 | 30 | 15 | 30 | 10 | 165 | 15 | 10 | 5 | 30 | 5
Number of Open Issues |  |  | #REF! |  | Planned Start Time | 7:30 | 7:35 | 7:40 | 7:50 | 8:00 | 8:05 | 8:15 | 8:30 | 9:00 | 9:30 | 9:45 | 10:00 | 10:30 | 10:40 | 11:00 | 11:30 | 11:45 | 11:45 | 11:45 | 12:15 | 12:30 | 12:45 | 12:55 | 13:25 | 13:40 | 14:10 | 14:20 | 17:05 | 17:20 | 17:30 | 17:35 | 18:05
Number of Closed Issues |  |  | #REF! |  | Planned End Time | 7:35 | 7:40 | 7:50 | 8:00 | 8:05 | 8:15 | 8:30 | 9:00 | 9:30 | 9:45 | 10:00 | 10:30 | 10:40 | 11:00 | 11:30 | 11:45 | 11:45 | 11:45 | 12:15 | 12:30 | 12:45 | 12:55 | 13:25 | 13:40 | 14:10 | 14:20 | 17:05 | 17:20 | 17:30 | 17:35 | 18:05 | 18:10
Total Number of Issues Logged |  |  | #REF! |  | Actual Start Time | ST | [6 empty] | ST |  |  |  | ST |  |  | ST | [7 empty] | ST |  |  |  | ST
[5 empty] | Actual End Time | [6 empty] | ET |  |  |  | ET |  |  | ET | [7 empty] | ET |  |  |  | ET | [5 empty] | ET
[5 empty] | Resource Performing Task | xxxx | xxxx | xxxx | TBC | xxxx | TBC | TBC | Refer to App Contacts | TBC | Refer to App Contacts | xxxx | xxxx | xxxx | xxxx | xxxx | xxxx | xxxx/DNS | xxxx | xxxx | xxxx | xxxx | xxxx | TBC/Refer to App Contacts | Refer to App Contacts | Refer to App Contacts | xxxx | Refer to App Contacts | xxxx | xxxx | xxxx | Refer to App Contacts | xxxx/xxxx
[6 empty] | Migration Kickoff Tasks | [6 empty] | Application Shutdown |  |  |  | Server Shutdown |  |  | VM Cutover | [7 empty] | Application Startup |  |  |  | Application Testing / Migration completion
VM | Function/Role | Move Group | Sequence | OS | VM Migration % Complete | Open Command Bridge and Take Role | Ensure Migration Readiness - Final GO/NO-GO | Confirm Data Replications are completed | Confirm Backups are completed | Confirm T-Minus (T-7 to T-0) are completed | Disable Alerts | Disable the Backup | Application Shutdown Tasks | Database Shutdown Tasks | Stop the services (various applications) and put them manual startup/Disable mode | Verify that all application/database/service shutdown tasks have been completed | Shutdown the VMs - CMO | Ensure that there is no activity on the VMs in CMO | Verify that the consistency group is in Active (sync) state between CMO & FMO | Enable Image Access on the CG | Power On the VMs of the CG at the FMO | Update internal/external DNS / LB entries as required (If Applicable) | Perform any remediation required(If Applicable) | Perform server boot healthcheck on VMs | Release to OS team for validation | Validate server tooling | Handover Server for User Acceptance Testing | Complete Database Startup Tasks | Start the services (various applications) and put them automatic startup mode as required | Complete Application Startup Tasks | Validate all application startup tasks are complete | Complete Operational Application Testing per UAT Document | Validate all application testing completed successfully | Enable Direct access on the Consistency Group at FMO | Cleanup the Consistency Group in RP4VM | Complete Application Testing (Business Testing) | Migration Complete Sign Off
Server01 | DB | Wave 00A | None | Windows | 90.625 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Pending | Pending | Pending
Server02 | App | Wave 00A | None | Windows | 90.625 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Pending | Pending | Pending
Server03 | App | Wave 00A | None | Windows | 9.375 | Complete | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | Complete | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | Complete | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | Pending | Pending | Pending
Server04 | App | Wave 00A | None | Windows | 9.375 | Complete | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | Complete | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | Complete | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | Pending | Pending | Pending
Server05 | App | Wave 00A | None | Windows | 9.375 | Complete | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | Complete | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | Complete | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | In-Progress | Pending | Pending | Pending
Server06 | App | Wave 00A | None | Windows | 84.375 | Complete | In-Progress | Pending | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Pending | Pending | Pending
Server07 | App | Wave 00A | None | Windows | 84.375 | Complete | In-Progress | Pending | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Pending | Pending | Pending
Server08 | App | Wave 00A | None | Windows | 84.375 | Complete | In-Progress | Pending | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Pending | Pending | Pending
Server09 | App | Wave 00A | None | Windows | 84.375 | Complete | In-Progress | Pending | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Pending | Pending | Pending

## Email Status Template Wave 00A (hidden)
Migration Communication Tracker | [6 empty] | Color Code
Note: | [6 empty] | On Track
Migration Command Center Bridge will be open during the complete cutover window | [6 empty] | Complete
Status Report to be shared via email every 1 hour | [6 empty] | Issue/Delay
If there are any issues/delays - The status frequency will be every hour or when there is an update, until the issue is fully resolved | [6 empty] | Delayed
Migration Name: | Migrate XX ABC Crop VM's currently existing in CMO Z1 to FMO Z2 | [5 empty] | Major Issue/Roll Back
Migration Status: | Not Started
Potential Delay | NO
RISK of Executing Backout Plan | NO
RISK of Exceeding Outage Window | NO
Migration Comment:
Migration Lead/Project Manager: | xxxx
Next Status Update | N/A
Runbook Link:
Next Steps:
Planned Outage Window | DD/MM/YYYY 08:00 EST | DD/MM/YYYY 20:00 EST |  |  | ON TRACK
Key Milestone Tracking | Planned Start Time | Planned End Time | Actual Start Time | Actual End Time | Status | Comments
Migration Kickoff Tasks |  |  | ST | ET | ON TRACK
Application Shutdown |  |  | ST | ET | ON TRACK
Server Shutdown |  |  | ST | ET | ON TRACK
VM Cutover |  |  | ST | ET | ON TRACK
Application Startup |  |  | ST | ET | ON TRACK
Application Testing |  |  | ST | ET | ON TRACK
0:00
[8 empty] | Migration Kickoff Tasks | 58.73% | Number of Open Issues | #REF! | Pending (By VM %) | 10.76%
[8 empty] | Application Shutdown | 75% | Number of Closed Issues | #REF! | In-Progress (By VM %) | 28.47%
[8 empty] | Server Shutdown | 66.67% | Total Number of Issues Logged | #REF! | Complete (By VM %) | 60.76%
[8 empty] | VM Cutover | 70.83%
[8 empty] | Application Startup | 66.67%
[8 empty] | Application Testing / Migration completion | 33.33%

## Tracker Sheet(Wave 00B) (hidden)
OVERALL STATUS % |  |  |  |  | Do Not Migrate (DNM) % | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | Pending (By VM %) | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
[5 empty] | In-Progress (By VM %) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | Complete (By VM %) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | Do Not Migrate (DNM) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  |  |  | Pending (By VM Count) | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
[5 empty] | In-Progress (By VM Count) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Complete (By VM Count) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Total VM Count | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13
[6 empty] | Migration Kickoff Tasks | [6 empty] | Application Shutdown |  |  |  | Server Shutdown |  |  | VM Cutover | [7 empty] | Application Startup |  |  |  | Application Testing / Migration completion
VM | Function/Role | Move Group | Sequence | OS | VM Migration % Complete | Open Command Bridge and Take Role | Ensure Migration Readiness - Final GO/NO-GO | Confirm Data Replications are completed | Confirm Backups are completed | Confirm T-Minus (T-7 to T-0) are completed | Disable Alerts | Disable the Backup | Complete Application Shutdown Tasks | Complete Database Shutdown Tasks | Stop the services (various applications) and put them manual startup/Disable mode | Verify that all application/database/service shutdown tasks have been completed | Shutdown the VMs - CMO | Ensure that there is no activity on the VMs in CMO | Verify that the consistency group is in Active (sync) state between CMO & FMO | Enable Image Access on the CG | Power On the VMs of the CG at the FMO | Update internal/external DNS / LB entries as required (If Applicable) | Perform any remediation required(If Applicable) | Perform server boot healthcheck on VMs | Release to OS team for validation | Validate server tooling | Handover Server for User Acceptance Testing | Complete Database Startup Tasks | Start the services (various applications) and put them automatic startup mode as required | Complete Application Startup Tasks | Validate all application startup tasks are complete | Complete Operational Application Testing per UAT Document | Validate all application testing completed successfully | Enable Direct access on the Consistency Group at FMO | Cleanup the Consistency Group in RP4VM | Complete Application Testing (Business Testing) | Migration Complete Sign Off
ESBBWSVCQ12 | App | Wave 00B | None | Windows | 0 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
HRSKROSQLD01 | DB | Wave 00B | None | Windows | 0 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
HRSKROWDMD01 | App | Wave 00B | None | Windows | 0 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
ESBADMINQ12 | App | Wave 00B | None | Windows | 0 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
ESBBWSVCQ13 | App | Wave 00B | None | Windows | 0 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
HRSKROWRMD01 | App | Wave 00B | None | Windows | 0 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
ESBADMINQ11 | App | Wave 00B | None | Windows | 0 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
ESBBWSVCQ11 | App | Wave 00B | None | Windows | 0 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
HRSKROAPPD01 | App | Wave 00B | None | Windows | 0 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
ESBEMSAPPCLQ11A | App | Wave 00B | None | Windows | 0 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
ESBEMSAPPCLQ11B | App | Wave 00B | None | Windows | 0 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
ESBEMSMONCLQ11A | App | Wave 00B | None | Windows | 0 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
ESBEMSMONCLQ11B | App | Wave 00B | None | Windows | 0 | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending

## Contorl M Migration Activities_
Task # | Activity | Applicability/DC | Task Description | Definition of Done | Performed By | App migration Plan | Comments - APP Team | Readiness/ Automated/manual | Current Status | Evidences
1 | Pre-Cutover | HK in GDC East Brown Estate | 14th Aug'25 - Brown DC - All jobs during the catalyst cutover window, Highlight all your critical jobs and its impacted app/reports business details - Implement a CR# CHG0820307 on or before 15TH AUG'25 2 PM HKT to mark NONE manual order in Brown PROD (manual deployment control-m team -- refer Misc Details) | -Forecast is taken for 14th Aug'25 - Highlighted in Red all jobs that are critical with their Impacted app/Dependent app and team | App Team/PSS | Forecast for 14th Aug'25 is in the sheet here with all impacted app Downstream and upstream. - Jobs that need to be put on HOLD due to HaaS platform cutover readiness are identified and highlighted in the forecast sheet attached with impacted app details. | Completed | Manual | Completed | N/A
2 | Pre-Cutover | HK in GDC East Brown Estate | Application Runbook is completed with all the Forecast data for the job to be executed on 15TH Aug'25 in Green DC . All jobs that need to be put on Hold for these dates due to overrun or Cutover time i.e. between 15TH Aug'25 8:00 PM to 16TH Aug'25 2025 7AM HKT are highlighted in the respective app runbook and are linked to the pre-cutover steps section in the runbook. Jobs with downstream dependency and Impact for business needs to be identified and should be part of the application runbook for each of the jobs for the respective app. | Forecast is taken for 15th Aug'25. Highlight the jobs in yellow if jobs that are critical with their Impacted/Dependent application and team. Hold job should be identified in different color or a sheet seperately.t | App Team/PSS | Forecast for 15th Aug'25 is in the sheet here with all impacted app Downstream and upstream. - AS part of Cutover strategy for ODATE 16TH Aug'25, all Control-m jobs in Brown will be marked to manual order by implmenting the CR as part of Step 3 in this doc. - No Manual jobs HOLD required as this will be taken care by CR which will get implemented on 15th Aug before 2 PM HKT. | Completed | Manual | In progress
3 | Pre-Cutover | HK in GDC East Brown Estate | Change readiness in approved state: Rais a CR for Marking the jobs in Manual order for Green DC. This CR should have 2 task each one for APp team and ATOS team. 1. App Team Task - Add a task in CR to Deploy jobs with NONE manual order using ADO pipeline in Brown DC. - should be performed by respective app team 2. App Team - App team can add a task to ATOS with the implementation plan (mentioned below) their in the runbook link for the following activity. The ATOS task will only be executed if App team fail to deploy using pipeline. The CR should be ready in approved state with above 2 task by 15th July 2025. should be raised and in approved state by 15th Aug 2025 and for the implementation date of 16TH Aug'25. | A CR to be ready with task for app team and backup task for ATOS CR Manual order and change to be implemented by ATOS. To be completed on 15th Aug'25. | App Team/PSS | CR is in New state. - Since every job for ODATE 15th is marked as NONE manual order via CR - CHG0820307, NONE of the jobs will get trigger automatically. Implement this CR only between 11 AM HKT -13 PM HKT in Brown on 15th Aug | CR Drafted . CR: CHG0820307 Start Date:14-08-2025 11 AM HKT End Date:16-08-2025 12 PM HKT you must implement your CR on 15th August before 2 PM PM HKT. -- Please make sure that you get the CR reviewed in draft stage itself with ATOS team before you submit it for approval.
4 | Pre-Cutover | HK in GDC East Brown Estate | Disable jobs/folders in Brown DC: To mark Jobs Manual NONE order - App team should use their CR as part of task #3 in this sheet to to deploy all jobs with NONE manual order starting 15th Aug'25 in Brown using ADO pipeline. - Failing to do so can use ATOS help to deploy manually. | Needs to be validated on 15th Aug post 2 PM HKT | App Team/PSS | In Progress to be implemented and validated post CR implementation | this needs to be validated on 15th Aug post 2 PM HKT | Manual | Completed
5 | Pre-Cutover | SG & HK | Green Control-M ready with Automatic schedule configured. Json Files has been prepared with Ordermethod Automatic Before freeze is exercised in Green Control-M site, App teams must Re-Deploy jobs in catalyst Green Control-M with automatic order method via ADO pipleline | 14th Aug'25 - Implement ADO pipeline to deploy in Green with automatic order (Manual task by control-m team -- refer Misc Details page for #RITM) Immediately after that activate WLP to suspend jobs from running in control-m from 15th August onward Note: This will result in jobs getting loaded everyday in control-m with WLP attached so that jobs does not trigger in active environment. This WLP will be valid until you deactivate it. Ideally you will deactive WLP only after GO/NO GO Call on cutover date. | App Team/PSS | In-Progress 14th Aug 2025 - on 14th August run the pipeline to deploy all your control-M jobs in Automatic order in Green. - Activate WLP post the implementation to suspend jobs from running until you deactivate it. 15th Aug 2025 - on 15th Aug at 7:10 AM HKT -8 AM HKT manually HOLD your jobs in Green as well. - you will also delete the jobs which are not supposed to be carried pver to Gereen DC on next day. i.e. you will delete all jobs for ODATE 15th in Green that has completed its run in Brown for ODATE 15th Aug. | NOTE: On 15th and 16th morning between 7:10 AM -7:30 AM HKT put Manual HOLD on all jobs in Green. On 15th Aug please delete all your jobs that does not require rerun in Green DC. (jobs that are scheduled before 4 PM run) | Automatic | Completed
6 | Pre-Cutover | SG & HK | Agent: ID Vaulting/EBM access and list of agents Agent: ID Vaulting/EBM access and list of agents to be verified. A screenshot confirming the same to be provided to Central team and Control-M team. | - Agent ID is vaulted and verified - A artifect is attached in this runbook. Attach a screenshot of vaulted ID in Word Doc and attach in this section | App Team/PSS | NA since it is going to be centrally taken care by HaaS platform team | NA | Manual | Completed
7 | Pre-Cutover | SG & HK | Hostgroups Creation and Configuration Host group - VIP DNC approach has been followed Hostgroups - Applications using host group and participation rules should review them in Control-M and sign off post validating the configuration, also need to provide the list of groups as well | - Host Groups should be created and configured in Control-M Site standards - A artifect is attached in this runbook. Attach a screenshot of vaulted ID in Word Doc and attach in this section | App Team/PSS | Task is completed and verified attached the artifects. | Completed | Manual | Completed
8 | Pre-Cutover | SG & HK | Job owner - Run as user | RunAs - Application teams to verify their RunAs users in their respective site standards | App Team/PSS | Task is completed and verified attached the artifects. | Completed | Manual | Completed
9 | Pre-Cutover | SG & HK | User Roles access verification | UserRoles - Applications to verify if members from application PSS/DEV teams are tagged to the correct AD groups. | App Team/PSS | Task is completed and verified attached the artifects. | Completed | Manual | Completed
10 | Pre-Cutover | SG & HK | Site Standard verification | Site Standard - App teams to verify their respective site standards and provide sign off that the details are up to date. Things to validate are primarily as below. Host/VIP names. RunAs ids. | App Team/PSS | Task is completed and verified attached the artifects. | Completed | Manual | Completed
11 | Pre-Cutover | SG & HK | Calendar Jobs verification Brown <-> Green Application team to login to Control-M and verify that the calendars are up to the date; Liaise with EBM for any updates in Catalyst Green DC | All calendars to be used in Green DC for your jobs are present and validated - A screen shot is attached as a artifects - Calendar details are submitted in this link to Control-M for validation | App Team/PSS | NA - Global calenders used | Global Calender. | NA | NA
12 | Pre-Cutover | SG & HK | QR verification Application team to login to Control-M and verify that their QR's are available and up to date; Liaise with EBM for any updates in Catalyst Green DC | Application team to login to Control-M and verify that their QR's are available and up to date; Liaise with EBM for any updates in Catalyst Green DC - Not appliable | App Team/PSS | Task is completed and verified attached the artifects. | Its verified and artifecect link is here https://dev.azure.com/sc-ado/TTOQPR/_workitems/edit/9901833 | Manual | Completed | https://dev.azure.com/sc-ado/TTOQPR/_workitems/edit/9901833
13 | Pre-Cutover | SG & HK | Global Conditions Not applicable for CARD400 Global Condition - Applications using global conditions(condition flow between 2 Control-M servers | Not Applicable | App Team/PSS | Not applicable |  | NA | NA
14 | Pre-Cutover | SG & HK | Job Alerts ITRS Job alerting rules: CTM ALERT MAPPING - alert rule mapping details to all applications for them to confirm on the alert routing for batch jobs failures. Liaise with EBM for updates in Catalyst Green DC | - The alert mapping rule shared by EBM has been verified - Any change required in TSO group should be notified and implemented with the help of Control-M team | App Team/PSS | During go live this activity should get kick started |  | Manual | Yet to Start
15 | Pre-Cutover | SG & HK | User Daily Job details User Daily - applications who have specific user daily to load their jobs in AJF outside of NDP should share us the user daily details for validation. Detail to share as below: user daily name and the time the jobs should be ordered Liaise with EBM for any updates in Catalyst Green DC | Not Applicable | App Team/PSS | Not applicable |  | NA | NA
16 | Pre-Cutover | SG & HK | PSS Team has validated Dynamic WLP in catalyst Green DC Dynamic WLP to be created and kept ready; Liaise with EBM for any updates in Catalyst Green | - Dynamic WLP is created and verified - Artifect is attached. | App Team/PSS | IN Progress |  | Manual | Yet to Start
17 | Pre-Cutover | SG & HK | Brown DC to Green DC dependency - Applicable to HaaS dependent apps | Brown DC to Green DC dependency - Applicable to HaaS dependent apps | App Team/PSS | Not applicable |  | NA | Done
18 | Cutover | Green DC | 16th Aug - Green DC - Manually order all jobs which were on HOLd in brown for 16TH Aug'25 in Green, complete them. | -Forecast is taken for 16th Aug'25 - Highlighted in Red all jobs that are critical with their Impacted app/Dependent app and team - Jobs were on hold on 16th are part of Green DC forecast list - BVT and tech test cases are associated with all your jobs and its deliverables | App Team/PSS | Forecast is attached for ODATE 16th Aug. - On 16th Aug at 7:10 AM HKT manually hold all your jobs for 16th Aug also. Please NOTE: WLP is still active for your app jobs so you will have to manually HOLD on top of it to make sure all jobs does not start at once. Group A: 9 AM HKT - Release WLP for all jobs at 9 AM HKT once Group A testing is called out to begin. - Run your jobs for (ODATE 15th) in Group A for Test purpose only by releasing them manually (only for the jobs that you want to run as part of testing). ideally some jobs which can assure you that cutover is running fine. Group B: 10 AM HKT - Run your jobs for (ODATE 15th) in Group B for Test purpose only by releasing them manually (the left over job for ODATE 15th to run as part of testing). post GO NO Go Call - Group C Testing - BAU - Release manual HOLD from ODATE 16th Aug JOb to let them run and continue with your BAU. | Completeds | Manual | Yet to Start
19 | Cutover | Green DC | 17 and 1t8h Aug'25 - Green DC - BAU in Hypercare - Job will execute as per its scheduling criteria | -Forecast is taken for 17 and 18th Aug'25 - Highlighted in yellow all jobs that are critical with their Impacted app/Dependent app and team | App Team/PSS | 17,18th Aug'25 jobs are highlighted in yellow. All BAU in HYPERCARE | Completed | Manual | Yet to Start
20 | Post Cutover | SG & HK | After successfull go live, work with atos to decom the app in brown Control-M; App team to submit the change as part of their brown dc decom. | Post Go Live - Brown Decomission Activites would be carried out -Change will be raised to ATOS for jobs Decommission | App Team/PSS | we will plan the CR for Decomm of Brown DC Control M jobs post Go live |  | Manual | Yet to Start

## Atos-Steady State POC's (hidden)
Name | Stream | Migration day Role/Responsibility | Company | Email id | POC(8 AM to 8 PM ET- 7th Nov) | Hypercare | POC(8 AM to 8 PM ET- 14th Nov) | Hypercare
xxxx (8am to 8pm EST) | Network Core | Oncall | vendor | xxxxx@ABC Crop.com | xxxx | xxxx, xxxx | xxxx | xxxx, xxxx
xxxx | Backup | Oncall | vendor | xxxxx@ABC Crop.com | dl-us-backup-networker dl-us-backup-networker@vendor.net (all except Z1) dl-my-nam-networker bkp team (Z1) | dl-us-backup-networker dl-us-backup-networker@vendor.net (all except Z1) dl-my-nam-networker bkp team (Z1) | dl-us-backup-networker dl-us-backup-networker@vendor.net (all except Z1) dl-my-nam-networker bkp team (Z1) | dl-us-backup-networker dl-us-backup-networker@vendor.net (all except Z1) dl-my-nam-networker bkp team (Z1)
xxxx | VMware Contact during execution | Oncall | vendor | xxxxx@ABC Crop.com | xxxx | xxxx | xxxx | xxxx
xxxx | VMware Contact during execution | Oncall | vendor | xxxxx@ABC Crop.com | xxxx | xxxx | xxxx | xxxx
xxxx | DNS | Oncall | vendor | xxxxx@ABC Crop.com | xxxx, dl-netman@vendor.net. | xxxx, dl-netman@vendor.net. | xxxx, dl-netman@vendor.net. | xxxx, dl-netman@vendor.net.
xxxx | DNS | Oncall | vendor | xxxxx@ABC Crop.com | xxxx | xxxx, dl-netman@vendor.net. | xxxx, dl-netman@vendor.net. | xxxx, dl-netman@vendor.net.
xxxx | Project Manager (vendor) | Required to Oversee Migration | vendor | xxxxx@ABC Crop.com | xxxx | xxxx | xxxx | xxxx
xxxx Long | Windows Team | Oncall | vendor | xxxxx@ABC Crop.com | xxxx Long | xxxx Long | xxxx Long | xxxx Long
xxxx | Windows Team | Oncall | vendor | xxxxx@ABC Crop.com | xxxx | xxxx | xxxx | xxxx
xxxx | Database - SQL | Oncall | vendor | xxxxx@ABC Crop.com | xxxx | xxxx | xxxx | xxxx
xxxx | SCOM for Active Directory Monitoring | Not used by ABC Crop | vendor | xxxxx@ABC Crop.com | Contact not required for Migration | Contact not required for Migration | Contact not required for Migration | Contact not required for Migration
xxxx | Security | Oncall | vendor | xxxxx@ABC Crop.com | Managed by ABC Crop | Managed by ABC Crop | ABC Crop | Managed by ABC Crop
xxxx | Security | Oncall | vendor | xxxxx@ABC Crop.com | Managed by ABC Crop | Managed by ABC Crop | ABC Crop | Managed by ABC Crop
xxxx | Security | Oncall | vendor | xxxxx@ABC Crop.com | Managed by ABC Crop | Managed by ABC Crop | ABC Crop | Managed by ABC Crop
xxxx | Nagios/BladeLogic | Required for Monitoring Tasks | vendor | xxxxx@ABC Crop.com | Automated/ABC Crop (WSUS) | Automated/ABC Crop (WSUS) | Automated | Automated/ABC Crop (WSUS)
xxxx | SPECTRUM for Network Monitoring | Oncall | vendor | xxxxx@ABC Crop.com | xxxx | xxxx | xxxx | xxxx
xxxx | Migration Architect | Oncall | vendor | xxxxx@ABC Crop.com | xxxx | xxxx | xxxx | xxxx
xxxx | SDM | Oncall | Steady State | xxxxx@ABC Crop.com | xxxx | xxxx | xxxx | xxxx
xxxx | Network | Oncall | Steady State | xxxxx@ABC Crop.com | xxxx | xxxx | xxxx | xxxx
xxxx | Network | Oncall | Steady State | xxxxx@ABC Crop.com | xxxx | xxxx | xxxx | xxxx
xxxx | Windows Team | Oncall | Steady State | xxxxx@ABC Crop.com | DL-ABC Crop-Windows@vendor.net | DL-ABC Crop-Windows@vendor.net | DL-ABC Crop-Windows@vendor.net | DL-ABC Crop-Windows@vendor.net
xxxx | Windows Team | Oncall | Steady State | xxxxx@ABC Crop.com | DL-ABC Crop-Windows@vendor.net | DL-ABC Crop-Windows@vendor.net | DL-ABC Crop-Windows@vendor.net | DL-ABC Crop-Windows@vendor.net

## Contact Numbers (hidden)
Name | Company | Role | Email ID | Contact
xxxx | ABC Crop | App Contacts | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | ABC Crop | App Contacts | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | ABC Crop | App Contacts | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | ABC Crop | App Contacts | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | DELL | Migration Execution Lead | xxxxx@dell.com | xxx-xxx-xxxx
xxxx | DELL | Dell Program Manager | xxxxx@dell.com | xxx-xxx-xxxx
xxxx | DELL | Dell Project Manager | xxxxx@dell.com | xxx-xxx-xxxx
xxxx | DELL | Migration Lead | xxxxx@dell.com | xxx-xxx-xxxx
xxxx | DELL | Technical Architect | xxxxx@dell.com | xxx-xxx-xxxx
xxxx | DELL | Technical Architect | xxxxx@dell.com | xxx-xxx-xxxx
xxxx | DELL | Execution Arthitect | xxxxx@dell.com | xxx-xxx-xxxx
xxxx (8am to 8pm EST) | Customer/Atos | Network Core | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | Backup | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | VMware Contact during execution | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | VMware Contact during execution | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | DNS | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | DNS | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | Project Manager (vendor) | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | Windows Team | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | Windows Team | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | Database - SQL | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | SCOM for Active Directory Monitoring | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | Security | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | Security | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | Security | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | Nagios/BladeLogic | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | Migration Architect | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | SDM | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | Network | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | Network | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | Windows Team | xxxxx@ABC Crop.com | xxx-xxx-xxxx
xxxx | Customer/Atos | Windows Team | xxxxx@ABC Crop.com | xxx-xxx-xxxx

## Storage Details (hidden)
Purpose: The purpose of this worksheet is to document and confirm all storage devices associated with target migration servers are identified and incorporated into a detailed data migration strategy which will be executed during the migration event.
Server Name | Datacenter | Logical Drive/Volume | Storage Type | Storage Frame | Allocated (MB) | Utilized (MB) | Volume Type/Purpose | Target Server Name | Target Server Datacenter | Target Logical Drive/Volume | Target Storage Type | Target Storage Frame | Target Allocated (MB) | Target Volume Type/Purpose | Target Storage Datacenter

## Contacts (hidden)
Purpose The purpose of this document is to provide a contact list that can be leveraged on the night of go live in the event that of an unexpected situation.
Name | Company | Role / Responsibility | POC | Email | Cell Phone
Michael Hale | Atos | Network Core | Michael Hale | michael.hale@atos.net | ?
Brian.Hansen; Kamaruddin, Khairul Nizar | Atos | Storage Team | Brian.Hansen; Kamaruddin, Khairul Nizar | brian.hansen@atos.net; Kamaruddin, Khairul Nizar <khairulnizar.kamaruddin@atos.net> | ?
Michael Key | Atos | Cloud- Compute HCI | Michael Key | michael.key@atos.net
Brian Hansen, Kamaruddin, Khairul Nizar | Atos | Cloud- Storage HCI | Brian Hansen, Kamaruddin, Khairul Nizar | brian.hansen@atos.net; khairulnizar.kamaruddin@atos.net
Hassan Ramadan, David Pena | Atos | HCI | Hassan Ramadan, David Pena | hassan.ramadan@atos.net; david.pena@atos.net
Sunil Singh | Atos | Unix Contact during execution - TBC | Sunil Singh | Sunil.2.singh@atos.net | ?
Willie McCaster | Atos | Backup Contact during execution | Willie McCaster | willie.mccaster@atos.net | ?
ennoch-ernesto.ortiz; werner.oroxon | Atos | VMware Contact during execution | ennoch-ernesto.ortiz; werner.oroxon | ennoch-ernesto.ortiz@atos.net; werner.oroxon@atos.net | ?
Billy Thomas | Atos | Monitoring during Execution | Billy Thomas | billy.thomas@atos.net | ?
Curtis Deslatte;chandrashekar.yanamandra | Atos | DNS | Curtis Deslatte;chandrashekar.yanamandra | Curtis.Deslatte@atos.net;chandrashekar.yanamandra@atos.net | ?
Project Manager (Atos) | Atos | PM for Execution | Mike Kulich | michael.kulich@atos.net | ?
BAU Team | Atos | Creating Tickets during Execution | DL Emails | dl-pittsburgh-hardware.team@atos.net / dl-blythewood-hardware.team_ito@atos.net, Blythewood: 803-626-3875 | ?
Hypercare Lead | Atos | Manage Hypercare post Execution | Mike Kulich | michael.kulich@atos.net | ?
Windows Team Contact | Atos | Windows Contact during execution | Mike Long / Chris Opie | mike.long@atos.net , chris.opie@atos.net | ?
Sunil Singh | Atos | Wintel - US | Sunil Singh | Sunil.2.singh@atos.net
Jeff Hall | Atos | Facilities Source DC | Jeff Hall | jeffrey.hall2@atos.net
Mike Watkins | Atos | Facilities Target DC | Mike Watkins | mike.watkins@atos.net
Juan Briones | Atos | Database - Oracle | Juan Briones | juan.briones@atos.net
Haidar Zalghout | Atos | Database - SQL | Haidar Zalghout | haidar.zalghout@atos.net
Unix Team Contact | Atos | OSE - Linux/Solaris/Unix | Unix Team Contact | ronald.phillips2@atos.net; anthony.chinn@atos.net;ashish.purna@atos.net
AIX Team Contact | Atos | OSE - AIX | AIX Team Contact | emiliano.roncaglia@atos.net, sudhakar.shanmugam@atos.net
John Jett | Atos | OSE - Backup Advertisement | John Jett | john.jett@atos.net
Prashant Mahajan | Atos | SCOM for Active Directory Monitoring | Prashant Mahajan | prashant.mahajan@atos.net
Corey Perkins | Atos | Security | Corey Perkins | corey.perkins@atos.net
Sagar Gawade, Ty Hollins | Atos | Security | Sagar Gawade, Ty Hollins | ty.hollins@atos.net; sagar.gawade@atos.net
Leif Stembol | Atos | Tools Team Monitoring during Execution (NAGIOS) | Leif Stembol | leif.stembol@atos.net
Ryan Boss | Atos | Bladelogic - Validation | Ryan Boss | ryan.boss@atos.net
BAU Team | Atos | BAU Lead | Thomas Rausch | thomas_rausch@atos.net
Sebastian Haszcz | Atos | SPECTRUM for Network Monitoring | Sebastian Haszcz | sebastian.haszcz@atos.net
Greg Hewko | CarMax | Application Owner | Prasana Parthiban and Chris Boyce | prasanna_parthiban@carmax.com, chris_boyce@carmax.com | ?
Steve Wheeler | CarMax | Application Owner | Abhishek Ghosh | abhishek_ghosh@carmax.com | ?
Brandyn Brown | CarMax | Application Owner | Brandyn Brown | brandyn_brown@carmax.com | ?
Michael Gangeri | CarMax | Application Owner | Blaise Gregory and Chelsea Moore | blaise_gregory@carmax.com, chelsea_a_moore@carmax.com | ?
Bryan Burgess | CarMax | Application Owner | Bryan Burgess, Prasanna | bryan_burgess@carmax.com;prasanna_parthiban@carmax.com
Matt Barnes | CarMax | Business Owner | Prasana Parthiban and Chris Boyce | prasanna_parthiban@carmax.com, chris_boyce@carmax.com | ?
Kerry Clendenon | CarMax | Business Owner | Jim Madison | jim_madison@carmax.com | ?
Blaise Gregory | CarMax | Business Owner | Blaise Gregory | blaise_gregory@carmax.com | ?
Prasanna Parthiban | CarMax | App Technical Contact/UAT | Prasanna Parthiban | prasanna_parthiban@carmax.com | ?
Jim Madison | CarMax | App Technical Contact/UAT | Jim Madison | jim_madison@carmax.com | ?
Daniel Peel | CarMax | App Technical Contact/UAT | Blaise Gregory and Chelsea Moore | blaise_gregory@carmax.com, chelsea_a_moore@carmax.com | ?
Greg Hewko | CarMax | Database Owner | Prasana Parthiban and Chris Boyce | prasanna_parthiban@carmax.com, chris_boyce@carmax.com | ?
Jarred Ford | CarMax | Database Owner | Shawn Beck and Brian Dittore | shawn_c_beck@carmax.com, brian_k_dittore@carmax.com | ?
Project Manager (Carmax) | CarMax | PM for Execution | David Bittenbender | david_c_bittenbender@carmax.com | ?
Hypercare Lead | Carmax | Manage Hypercare post Execution | David Bittenbender, Greg Ballard | david_c_bittenbender@carmax.com, greg_ballard@carmax.com | ?
Oracle & SQL Contact | Carmax | Database Owner | ? | ? | ?
Asif Pasha | Dell | Migration lead | Asif Pasha | Asif.Pasha@Dell.com | 91-994 521 5633
Ashoka Reddy | Dell | Migration Architech | Ashoka Reddy | Ashoka.Reddy@Dell.com | ?
Hemang Mehta | Dell | Project Manager | Hemang Mehta | Hemang.Mehta@dell.com | 91-983 359 5863
Sarvana/Manju | Dell | Perform Migration Execution | Sarvana/Manju | ? | ?
Hypercare Lead | Dell | Manage Hypercare post Execution | Need Contact | ? | ?
Srinivas Veeramachaneni | Dell | Global Solutions Architect | Srinivas Veeramachaneni | Srinivas.Veeramachan@Dell.com
Avia Banks | Dell | Global Program Manager | Avia Banks | Avia.Banks@dell.com
Long Luong | Steady State | SDM | Long Luong | long.luong@atos.net
Carlos Almiray | Steady State | Network | Carlos Almiray | carlos.almiray@atos.net
Keith Jackson | Steady State | Network | Keith Jackson | keith.2.jackson@atos.net
Ganapati Hegde | Steady State | Wintel | Ganapati Hegde | ganapati.hegde@atos.net
Prashanth K Wagle | Steady State | Wintel | Prashanth K Wagle | prashanth.k@atos.net

## ControlM_Cutover_jobs
S.No | Job name | Description | Run | Date | Parent folder | Upstream | Command
1 | SGM_GBL_UPDREPDT | Reporting date update | Others | CD1 | SGM_E_GBL_BATCH | NA | $script_path/jbs_refresh_current_reporting_period.sh
2 | SGM_GBL_TABLUDATFULLREF | Tableau Refresh | Others | CD1 | SGM_E_GBL_BATCH | NA | $script_path/tableau_24months_refresh.sh %%job_group
3 | SGM_GBL_PRASTGEARLY17 | Staging job | PRA Flash | CD5 To CD8 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
4 | SGM_GBL_DMYRMIEARLY | Dummy job will completed after wating window over | RMI | CD6 To CD9 | SGM_E_GBL_BATCH | RMI
5 | SGM_GBL_RMISTGEARLY | Staging job | RMI | CD6 To CD9 | SGM_E_GBL_BATCH | RMI | $script_path/jbs_sgmi_rmi_stg_filewatcher.sh %%daily_monthly_flag STG %%system %%country %%NEXT_SCH
6 | SGM_GBL_RMIFNDPLPEARLY | FND PLP |  | CD6 To CD9 | SGM_E_GBL_BATCH | RMI | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND %%system %%country
7 | SGM_GBL_PRADMY7 | Dummy job will completed after wating window over | PRA Main | CD9 To CD11 | SGM_E_GBL_BATCH | BCRS
8 | SGM_GBL_PRASTGMN7_FW | Staging job | PRA Main | CD9 To CD11 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
9 | SGM_GBL_PRAFNDPLPMN7 | FND PLP | PRA Main | CD9 To CD11 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
10 | SGM_GBL_PRAOUTMN7 | TDS Extract | PRA Main | CD9 To CD11 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace
11 | SGM_GBL_PRADMY9 | Dummy job will completed after wating window over | PRA Main | CD9 To CD11 | SGM_E_GBL_BATCH | BCRS
12 | SGM_GBL_STGPRAMN9_FW | Staging job | PRA Main | CD9 To CD11 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
13 | SGM_GBL_FNDPLPPRAMN9 | FND PLP | PRA Main | CD9 To CD11 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
14 | SGM_GBL_OUTPRAMN9 | TDS Extract | PRA Main | CD9 To CD11 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace
15 | SGM_GBL_MFUSTG | Staging job | MFU | CD10 | SGM_E_GBL_BATCH | BCRS | $script_path/sgmi_stg_MFU.sh
16 | SGM_GBL_MFUFNDPLP | FND PLP |  | CD10 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country
17 | SGM_SG_NDDMY29 | Dummy job will completed after wating window over | ND Main | CD11 To CD12 | SGM_E_GBL_BATCH | BCRS
18 | SGM_SG_NDSTGMN29_FW | Staging job | ND Main | CD11 To CD12 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
19 | SGM_SG_NDFNDPLPMN29 | FND PLP | ND Main | CD11 To CD12 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
20 | SGM_SG_NDOUTMN29 | TDS Extract | ND Main | CD11 To CD12 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace
21 | SGM_SG_NDDMY36 | Dummy job will completed after wating window over | ND Main | CD11 To CD12 | SGM_E_GBL_BATCH | BCRS
22 | SGM_SG_NDSTGMN36_FW | Staging job | ND Main | CD11 To CD12 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
23 | SGM_SG_NDFNDPLPMN36 | FND PLP | ND Main | CD11 To CD12 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
24 | SGM_SG_NDOUTMN36 | TDS Extract | ND Main | CD11 To CD12 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace
25 | SGM_SG_RCDMY42 | Dummy job will completed after wating window over | RC Main | CD12 To CD13 | SGM_E_GBL_BATCH | BCRS
26 | SGM_SG_RCSTGMN42 | Staging job | RC Main | CD12 To CD13 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
27 | SGM_SG_RCFNDPLPMN42 | FND PLP | RC Main | CD12 To CD13 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
28 | SGM_SG_RCOUTMN42 | TDS Extract | RC Main | CD12 To CD13 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace
29 | SGM_SG_RCDMY43 | Dummy job will completed after wating window over | RC Main | CD12 To CD13 | SGM_E_GBL_BATCH | BCRS
30 | SGM_SG_RCSTGMN43 | Staging job | RC Main | CD12 To CD13 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
31 | SGM_SG_RCFNDPLPMN43 | FND PLP | RC Main | CD12 To CD13 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
32 | SGM_SG_RCOUTMN43 | TDS Extract | RC Main | CD12 To CD13 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace
33 | SGM_GBL_RMIDMYMM | Dummy job will completed after wating window over | RMI | CD15 To CD20 | SGM_E_GBL_BATCH | RMI | $script_path/jbs_sgmi_rmi_stg_filewatcher.sh %%daily_monthly_flag STG %%system %%country %%NEXT_SCH
34 | SGM_GBL_RMISTGMN | Staging job | RMI | CD15 To CD20 | SGM_E_GBL_BATCH | RMI | $script_path/jbs_sgmi_rmi_stg_filewatcher.sh %%daily_monthly_flag STG %%system %%country %%NEXT_SCH
35 | SGM_GBL_RMIFNDPLPMN | FND PLP | RMI | CD15 To CD20 | SGM_E_GBL_BATCH | RMI | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND %%system %%country
36 | SGM_GBL_PRADMY7A | Dummy job will completed after wating window over | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS
37 | SGM_GBL_PRAFLCPYFW7A_FW | Copy files for Adj run | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher_adj.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
38 | SGM_GBL_PRASTG7A | Staging job | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_ingestion.sh %%daily_monthly_flag STG %%system %%country %%workspace
39 | SGM_GBL_PRAFNDPLP7A | FND PLP | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
40 | SGM_GBL_PRAOUT7A | TDS Extract | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace
41 | SGM_GBL_PRADMY9A | Dummy job will completed after wating window over | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS
42 | SGM_GBL_PRAFLCPYFW9A_FW | Copy files for Adj run | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher_adj.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
43 | SGM_GBL_PRASTG9A | Staging job | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_ingestion.sh %%daily_monthly_flag STG %%system %%country %%workspace
44 | SGM_GBL_PRAFNDPLP9A | FND PLP | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
45 | SGM_GBL_PRAOUT9A | TDS Extract | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace
46 | SGM_SG_NDDMY29A | Dummy job will completed after wating window over | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS
47 | SGM_SG_NDFLCPYFW29A_FW | Copy files for Adj run | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher_adj.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
48 | SGM_SG_NDSTG29A | Staging job | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_ingestion.sh %%daily_monthly_flag STG %%system %%country %%workspace
49 | SGM_SG_NDFNDPLP29A | FND PLP | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
50 | SGM_SG_NDOUT29A | TDS Extract | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace
51 | SGM_SG_NDDMY36A | Dummy job will completed after wating window over | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS
52 | SGM_SG_NDFLCPYFW36A_FW | Copy files for Adj run | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher_adj.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
53 | SGM_SG_NDSTG36A | Staging job | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_ingestion.sh %%daily_monthly_flag STG %%system %%country %%workspace
54 | SGM_SG_NDFNDPLP36A | FND PLP | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
55 | SGM_SG_NDOUT36A | TDS Extract | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace
56 | SGM_SG_RCDMY42A | Dummy job will completed after wating window over | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS
57 | SGM_SG_RCFLCPYFW42A_FW | Copy files for Adj run | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher_adj.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
58 | SGM_SG_RCSTG42A | Staging job | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_ingestion.sh %%daily_monthly_flag STG %%system %%country %%workspace
59 | SGM_SG_RCFNDPLP42A | FND PLP | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
60 | SGM_SG_RCOUT42A | TDS Extract | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace
61 | SGM_SG_RCDMY43A | Dummy job will completed after wating window over | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS
62 | SGM_SG_RCFLCPYFW43A_FW | Copy files for Adj run | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher_adj.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
63 | SGM_SG_RCSTG43A | Staging job | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_ingestion.sh %%daily_monthly_flag STG %%system %%country %%workspace
64 | SGM_SG_RCFNDPLP43A | FND PLP | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
65 | SGM_SG_RCOUT43A | TDS Extract | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace
66 | SGM_GBL_DATHSKP | Housekeeping | HK | CD28 | SGM_E_GBL_BATCH | NA | $script_path/jbs_sgmi_housekeeping_run.sh
67 | SGM_GBL_FLHSKP | Housekeeping | HK | CD28 | SGM_E_GBL_BATCH | NA

## SGMI Jobs(All)
Seq. | Job Name | Description | Run | Usual Run date | Parent Folder
1 | SGM_GBL_UPDREPDT | Reporting date update | Others | CD1 | SGM_E_GBL_BATCH
2 | SGM_GBL_TABLUDATFULLREF | Tableau Refresh | Others | CD1
| SGM_GBL_PRASTGEARLY17 | Staging job | PRA Flash | CD5 To CD8
0 | SGM_GBL_DMYRMIEARLY | Dummy job will completed after wating window over | RMI | CD6 To CD9 | 7 9 29 36 42 43
1 | SGM_GBL_RMISTGEARLY | Staging job | RMIRMI | CD6 To CD9
2 | SGM_GBL_RMIFNDPLPEARLY | FND PLP |  | CD6 To CD9
0 | SGM_GBL_PRADMY7 | Dummy job will completed after wating window over | PRA Main | CD9 To CD11
1 | SGM_GBL_PRASTGMN7_FW | Staging job | PRA Main | CD9 To CD11
2 | SGM_GBL_PRAFNDPLPMN7 | FND PLP | PRA Main | CD9 To CD11
3 | SGM_GBL_PRAOUTMN7 | TDS Extract | PRA Main | CD9 To CD11
0 | SGM_GBL_PRADMY9 | Dummy job will completed after wating window over | PRA Main | CD9 To CD11
1 | SGM_GBL_STGPRAMN9_FW | Staging job | PRA Main | CD9 To CD11
2 | SGM_GBL_FNDPLPPRAMN9 | FND PLP | PRA Main | CD9 To CD11
3 | SGM_GBL_OUTPRAMN9 | TDS Extract | PRA Main | CD9 To CD11
1 | SGM_GBL_MFUSTG | Staging job | MFU | CD10 | Need to trigger
2 | SGM_GBL_MFUFNDPLP | FND PLP |  | CD10
0 | SGM_SG_NDDMY29 | Dummy job will completed after wating window over | ND Main | CD11 To CD12
1 | SGM_SG_NDSTGMN29_FW | Staging job | ND Main | CD11 To CD12
2 | SGM_SG_NDFNDPLPMN29 | FND PLP | ND Main | CD11 To CD12
3 | SGM_SG_NDOUTMN29 | TDS Extract | ND Main | CD11 To CD12
0 | SGM_SG_NDDMY36 | Dummy job will completed after wating window over | ND Main | CD11 To CD12
1 | SGM_SG_NDSTGMN36_FW | Staging job | ND Main | CD11 To CD12
2 | SGM_SG_NDFNDPLPMN36 | FND PLP | ND Main | CD11 To CD12
3 | SGM_SG_NDOUTMN36 | TDS Extract | ND Main | CD11 To CD12
0 | SGM_SG_RCDMY42 | Dummy job will completed after wating window over | RC Main | CD12 To CD13
1 | SGM_SG_RCSTGMN42 | Staging job | RC Main | CD12 To CD13
2 | SGM_SG_RCFNDPLPMN42 | FND PLP | RC Main | CD12 To CD13
3 | SGM_SG_RCOUTMN42 | TDS Extract | RC Main | CD12 To CD13
0 | SGM_SG_RCDMY43 | Dummy job will completed after wating window over | RC Main | CD12 To CD13
1 | SGM_SG_RCSTGMN43 | Staging job | RC Main | CD12 To CD13
2 | SGM_SG_RCFNDPLPMN43 | FND PLP | RC Main | CD12 To CD13
3 | SGM_SG_RCOUTMN43 | TDS Extract | RC Main | CD12 To CD13
1 | SGM_GBL_RMIDMYMM | Dummy job will completed after wating window over | RMI | CD15 To CD20
0 | SGM_GBL_RMISTGMN | Staging job | RMI | CD15 To CD20
2 | SGM_GBL_RMIFNDPLPMN | FND PLP | RMI | CD15 To CD20
1 | SGM_GBL_PRADMY7A | Dummy job will completed after wating window over | PRA ADJ | CD15 To CD26
0 | SGM_GBL_PRAFLCPYFW7A_FW | Copy files for Adj run | PRA ADJ | CD15 To CD26
2 | SGM_GBL_PRASTG7A | Staging job | PRA ADJ | CD15 To CD26
3 | SGM_GBL_PRAFNDPLP7A | FND PLP | PRA ADJ | CD15 To CD26
4 | SGM_GBL_PRAOUT7A | TDS Extract | PRA ADJ | CD15 To CD26
0 | SGM_GBL_PRADMY9A | Dummy job will completed after wating window over | PRA ADJ | CD15 To CD26
1 | SGM_GBL_PRAFLCPYFW9A_FW | Copy files for Adj run | PRA ADJ | CD15 To CD26
2 | SGM_GBL_PRASTG9A | Staging job | PRA ADJ | CD15 To CD26
3 | SGM_GBL_PRAFNDPLP9A | FND PLP | PRA ADJ | CD15 To CD26
4 | SGM_GBL_PRAOUT9A | TDS Extract | PRA ADJ | CD15 To CD26
0 | SGM_SG_NDDMY29A | Dummy job will completed after wating window over | ND ADJ | CD20 To CD22
1 | SGM_SG_NDFLCPYFW29A_FW | Copy files for Adj run | ND ADJ | CD20 To CD22
2 | SGM_SG_NDSTG29A | Staging job | ND ADJ | CD20 To CD22
3 | SGM_SG_NDFNDPLP29A | FND PLP | ND ADJ | CD20 To CD22
4 | SGM_SG_NDOUT29A | TDS Extract | ND ADJ | CD20 To CD22
0 | SGM_SG_NDDMY36A | Dummy job will completed after wating window over | ND ADJ | CD20 To CD22
1 | SGM_SG_NDFLCPYFW36A_FW | Copy files for Adj run | ND ADJ | CD20 To CD22
2 | SGM_SG_NDSTG36A | Staging job | ND ADJ | CD20 To CD22
3 | SGM_SG_NDFNDPLP36A | FND PLP | ND ADJ | CD20 To CD22
4 | SGM_SG_NDOUT36A | TDS Extract | ND ADJ | CD20 To CD22
0 | SGM_SG_RCDMY42A | Dummy job will completed after wating window over | RC ADJ | CD22 To CD26
1 | SGM_SG_RCFLCPYFW42A_FW | Copy files for Adj run | RC ADJ | CD22 To CD26
2 | SGM_SG_RCSTG42A | Staging job | RC ADJ | CD22 To CD26
3 | SGM_SG_RCFNDPLP42A | FND PLP | RC ADJ | CD22 To CD26
4 | SGM_SG_RCOUT42A | TDS Extract | RC ADJ | CD22 To CD26
0 | SGM_SG_RCDMY43A | Dummy job will completed after wating window over | RC ADJ | CD22 To CD26
1 | SGM_SG_RCFLCPYFW43A_FW | Copy files for Adj run | RC ADJ | CD22 To CD26
2 | SGM_SG_RCSTG43A | Staging job | RC ADJ | CD22 To CD26
3 | SGM_SG_RCFNDPLP43A | FND PLP | RC ADJ | CD22 To CD26
4 | SGM_SG_RCOUT43A | TDS Extract | RC ADJ | CD22 To CD26
1 | SGM_GBL_DATHSKP | Housekeeping | HK | CD28
2 | SGM_GBL_FLHSKP | Housekeeping | HK | CD28

## Group A & B test Jobs
Group A Test Jobs | Group B Test Jobs

## 14Aug
NO JOBS for Aug 14 scheduled run (CD14)

## CD 15 to 20
S.No | Job name | Description | Run | Date | Parent folder | Upstream | Command
33 | SGM_GBL_RMIDMYMM | Dummy job will completed after wating window over | RMI | CD15 To CD20 | SGM_E_GBL_BATCH | RMI | $script_path/jbs_sgmi_rmi_stg_filewatcher.sh %%daily_monthly_flag STG %%system %%country %%NEXT_SCH
34 | SGM_GBL_RMISTGMN | Staging job | RMI | CD15 To CD20 | SGM_E_GBL_BATCH | RMI | $script_path/jbs_sgmi_rmi_stg_filewatcher.sh %%daily_monthly_flag STG %%system %%country %%NEXT_SCH
35 | SGM_GBL_RMIFNDPLPMN | FND PLP | RMI | CD15 To CD20 | SGM_E_GBL_BATCH | RMI | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND %%system %%country

## CD 15 to 26
S.No | Job name | Description | Run | Date | Parent folder | Upstream | Command
36 | SGM_GBL_PRADMY7A | Dummy job will completed after wating window over | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS
37 | SGM_GBL_PRAFLCPYFW7A_FW | Copy files for Adj run | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher_adj.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
38 | SGM_GBL_PRASTG7A | Staging job | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_ingestion.sh %%daily_monthly_flag STG %%system %%country %%workspace
39 | SGM_GBL_PRAFNDPLP7A | FND PLP | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
40 | SGM_GBL_PRAOUT7A | TDS Extract | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace
41 | SGM_GBL_PRADMY9A | Dummy job will completed after wating window over | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS
42 | SGM_GBL_PRAFLCPYFW9A_FW | Copy files for Adj run | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher_adj.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
43 | SGM_GBL_PRASTG9A | Staging job | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_ingestion.sh %%daily_monthly_flag STG %%system %%country %%workspace
44 | SGM_GBL_PRAFNDPLP9A | FND PLP | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
45 | SGM_GBL_PRAOUT9A | TDS Extract | PRA ADJ | CD15 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace

## CD 20 to 22
S.No | Job name | Description | Run | Date | Parent folder | Upstream | Command
46 | SGM_SG_NDDMY29A | Dummy job will completed after wating window over | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS
47 | SGM_SG_NDFLCPYFW29A_FW | Copy files for Adj run | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher_adj.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
48 | SGM_SG_NDSTG29A | Staging job | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_ingestion.sh %%daily_monthly_flag STG %%system %%country %%workspace
49 | SGM_SG_NDFNDPLP29A | FND PLP | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
50 | SGM_SG_NDOUT29A | TDS Extract | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace
51 | SGM_SG_NDDMY36A | Dummy job will completed after wating window over | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS
52 | SGM_SG_NDFLCPYFW36A_FW | Copy files for Adj run | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher_adj.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
53 | SGM_SG_NDSTG36A | Staging job | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_ingestion.sh %%daily_monthly_flag STG %%system %%country %%workspace
54 | SGM_SG_NDFNDPLP36A | FND PLP | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
55 | SGM_SG_NDOUT36A | TDS Extract | ND ADJ | CD20 To CD22 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace

## CD 22 to 26
S.No | Job name | Description | Run | Date | Parent folder | Upstream | Command
56 | SGM_SG_RCDMY42A | Dummy job will completed after wating window over | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS
57 | SGM_SG_RCFLCPYFW42A_FW | Copy files for Adj run | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher_adj.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
58 | SGM_SG_RCSTG42A | Staging job | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_ingestion.sh %%daily_monthly_flag STG %%system %%country %%workspace
59 | SGM_SG_RCFNDPLP42A | FND PLP | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
60 | SGM_SG_RCOUT42A | TDS Extract | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace
61 | SGM_SG_RCDMY43A | Dummy job will completed after wating window over | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS
62 | SGM_SG_RCFLCPYFW43A_FW | Copy files for Adj run | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_filewatcher_adj.sh %%daily_monthly_flag STG %%system %%country %%workspace %%NEXT_SCH
63 | SGM_SG_RCSTG43A | Staging job | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_stg_ingestion.sh %%daily_monthly_flag STG %%system %%country %%workspace
64 | SGM_SG_RCFNDPLP43A | FND PLP | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_sgmi_fnd_plp.sh %%daily_monthly_flag FND:PLP %%system %%country %%workspace
65 | SGM_SG_RCOUT43A | TDS Extract | RC ADJ | CD22 To CD26 | SGM_E_GBL_BATCH | BCRS | $script_path/jbs_tableau_out_refresh.sh %%daily_monthly_flag OUT %%system %%country %%workspace

## Misc Details
Application | SGMI (Full HaaS)
ITAM ID | 50896
Catalyst event | 3.5
Control-M server | hklvapapp640
Environment | Brown
Folder | SGM_E_GBL_BATCH
Number of jobs | 67
SiteStandard | SGMI_PROD
OrderMethod | Manual
RITM number | RITM3898860
workspace name | catalyst migration prod 640
xml file | catalyst migration prod 640.xml

## Host Remediation (hidden)
TOC
Migration Planning Workbook Host Remediation Recommendations
ME | Server | Status | Current HBA Driver | Current Firmware | Current Boot Bios | Required HBA Driver | Required Firmware | Required Boot Bios | Comments | Completion Status
[10 empty] | Red | Delayed
[10 empty] | Green | Completed
[10 empty] | Blue | In-Progress

## Application Dependencies (hidden)
TOC
Migration Planning Workbook Application Dependencies
Purpose: The purpose of this worksheet is to identify all internal and external application dependency touchpoints to ensure they are verified and tested prior to go live.
Primary Application | Primary Application Server | Related Application | Related Application Server | Interface Method | Interface Type | Frequency

## Status Update Template (hidden)
Current Migration Lead: Asif Pasha Manager on Duty: <Name> Current Status: GREEN - Potential Delay: No - Risk of Executing Back-Out Plan: No - Risk of Exceeding Outage Window: No Next Status Update: 04/14/2021, 2pm EST Milestone Tracking: - Application Shutdown: Completed (176 of 176) - Database Instance(s) Only Migrations: In Progress (1 of 1) - Forklift Migration: Completed (32 of 48) In Progress (16 of 48) - V2V Process: Completed (46 of 46) - P2V Process: Completed (4 of 4) - Application Startup and Test: Completed (20 of 176) , Not Started (3 of 176) , In-Progress (153 of 176) . Open Issues Details: Issue from Issues Log: #13 Closed Impacted Server(s): MOPPGPMEDWEBS1 Description – The ports are negotiating at 100 MBps instead of 1GBps Sun 9/24/17 – 02:15 AM EST – WebEx is created to troubleshoot the issue with Network/SiteServices and Unix (OS) team, WebEx: Sun 9/24/17 – 4:40 AM EST – A H/W vendor ticket is being opened. T&M Ref# GBL27628062i 9/24/17 – 10:00PM – There was a change made by Platform team in the configuration file and cable was connected to ce1 interface. Issue stands resolved now Migration Plan: Kindly check Event Runbook at: Link to Run Book Escalations: Contact Migration Leads directly with any issues during migration window Migration Event Lead: Asif Pasha / +91-9945215633 Migration Event Lead Secondary: <Name> / <Contact> Migration Manager: <Name> / <Contact>

## Hypercare Checklist (hidden)
Hypercare Checklist | Comments
Wave Name | Wave 00A
Hypercare Start Date
Hypercare Start time
Confirm the performance Network and Storage post migration at FMO
Hypercare End Date
Hypercare End time
Hypercare lead 1
Hypercare lead 2
Hypercare Project Manager
Migration RFC closed? Y/N
Number of Incidents open post migration window (Refer to 'Incident Tracking' tab)
Rollback Pending post migration window?
Application count of UAT Pending post migration window
Application count of Business testing pending post migrtion window
BAU support team contact
Hypercare Command Center Bridge link
Handoff complete between Migration lead and Hypercare Lead?
Risks if any for Hypercare
Are Vendors part of Hypercare? If yes then contact details required

## Glossary (hidden)
TOC
Migration Planning Workbook Glossary
Purpose: The purpose of this tab is to provide a list of terminology that is used in this migration runbook and will be used regularly by migration.
Migration Term | Term Description | Commonly Referred to as:
Migration Event (ME) | Defined as a move event or calendar dates during which applications are migrated. An ME can be comprise of one or more bundles. | Move Move Event Migration Weekend
Bundle | A bundle is a component of a wave. A bundle can be comprised of one or more applications.
Migration Planning Workbook | A Microsoft Excel workbook which is made up of multiple tabs that provides information about the migration. There will be one Migration Planning Workbook per bundle. Each Migration Planning Workbook contains detailed, tasks, contact information and anything related to a particular bundle. | Detailed Migration Plan
Command Center | The central location of the migration team during waves, usually a common room such as a conference room. Command Center contact information is included in each Migration Planning Workbook. | War Room
Contingency Plan | A series of steps that are triggerred by an unexpected result during the migration. Contingency plans usually go into effect when the result has a severe impact (level of severity defined by customer) on the migration. | Back Out Plan
Impacted Applications | Applications that are effected by the migration that may or may not be moving as part of the wave and/or migration.
Configuration Items | An item that is related to the migration, e.g. a server, an application, database, etc | Application Server
Pre Migration Task | Any action related to the migration that needs to be executed prior to the migration. | Prerequisite

## Status Summary (hidden)
TOC | [8 empty] | ME | Application Name | Application Owner | Server | Target Site | Migration Status | Migration Method | Operating System | Total Capacity (GB) | Total Used Space (GB) | Total Free Space (GB) | Server Type
Migration Event Summary
| Migration Status |  | Server Count
| Not Started |  | 0
| Completed |  | 0
| In-Progress |  | 0
| Rescheduled |  | 0
| Retired |  | 0
| Rolled Back |  | 0
| Other |  | 0
| Escalated L1 |  | 0
| Escalated L2 |  | 0
| Escalated L3 |  | 0
| Total |  | 0
Capacity Reporting Metrics
Capacity by Location
|  |  | Total Capacity (GB) |  | Total Used Space (GB) |  | Total Free Space (GB)
|  | Physical | #REF! |  | #REF! |  | #REF!
|  | Virtual | #REF! |  | #REF! |  | #REF!
|  | Total | #REF! |  | #REF! |  | #REF!
|  |  | Total Capacity (GB) |  | Total Used Space (GB) |  | Total Free Space (GB)
|  | Physical | #REF! |  | #REF! |  | #REF!
|  | Virtual | #REF! |  | #REF! |  | #REF!
|  | Total | #REF! |  | #REF! |  | #REF!
|  | Overall Total | #REF! |  | #REF! |  | #REF!
Status Reporting Metrics
Status of Total Progress
|  | Planned | Completed | Retired and Rescheduled
|  | 1 | #REF! | #REF!
Status by Location
|  |  | Completed | In-Progress | Not Started | L1 | L2 | L3
|  | Springfield | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Location 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Status by Operating System
|  |  | Completed | In-Progress | Not Started | L1 | L2 | L3
|  | Intel | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | HP-UX | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Linux | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Solaris | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Status by Migration Method
|  |  | Completed | In-Progress | Not Started | L1 | L2 | L3
|  | P&S | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | V2V | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Refresh | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | Total | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Server Count by Location
Server Count by Operating System
Server Count by Method of Migration