## Implementaion_Plan
Implementation Plan - CHG0820307
S. No | Activity | Task Owner | Start Date(IST) | End Date (IST)
1 | Withdraw EID | BMC Control-M HK Workflow Orchestration Prod TSO SUP | 2025-08-14 14:00 | 2025-08-17 14:00
2 | On mail confirmation from SCB Application, take backup of the below mentioned folders which is present in the submitted workspace in GDCE Control -M Production Server as part of the change CHG0820307: RITM Number : RITM3898860 Workspace Name : catalyst migration prod 640 | BMC Control-M HK Workflow Orchestration Prod TSO SUP | 2025-08-14 14:00 | 2025-08-17 14:00
3 | Atos EBM to check-in the approved workspace in Control-M Production. Note: If workspace not able to load at the time of implementation , then upload the xml which is attached in CR. | BMC Control-M HK Workflow Orchestration Prod TSO SUP | 2025-08-14 14:00 | 2025-08-17 14:00
Backout Plan - CHG0820307
S. No | Activity | Task Owner | Start Date(IST) | End Date (IST)
1 | On mail confirmation from SCB Application, ATOS EBM to restore all folders from the backup as mentioned in the above steps (Sr. no 2) into GDCE Control -M Production Server as part of the change CHG0820307 | BMC Control-M HK Workflow Orchestration Prod TSO SUP | 2025-08-14 14:00 | 2025-08-17 14:00